## README
Moya One website: project tracker
Hand this to the developer. Everything she needs to plan and report is in these tabs.
How to use
1. Dashboard: enter the kickoff date in the yellow cell. All task dates recalculate from it.
2. Tracker: one row per task. Update Status (dropdown) and Notes. Do not change IDs.
4. Client Inputs: everything we are waiting on from Omar. Chase these first.
5. Claims: every factual claim for the site, and whether it can be published yet.
Colour key
Design audit: after every change, the developer runs the taste and impeccable skills and fixes anything that looks vibe-coded. Record "Audit: pass" in Notes. See CLAUDE.md.
Yellow cell = editable input. Black text = formula, do not overwrite.
Status values
Not started, In progress, Blocked, Done. Mark Blocked and add the reason in Notes.
Kickoff date is Sat 24 Oct 2026. Change it if the agreement is signed later. Change it when the agreement is signed.
Day numbers are working days (Mon to Sat, Sunday off). Timeline: 4 weeks total (3 build, 1 test), per the call on 2026-10-22. Video is included in that window and is flagged as a risk.

## Dashboard
Moya One: dashboard
Kickoff date (edit) | 2026-10-24
Status | Tasks
Not started | 40
In progress | 0
Blocked | 0
Done | 0
Total tasks | 40
Percent done | 0%
Overdue (end date passed, not Done) | 0
Tasks waiting on client | 12
Project end date (last task) | 2026-11-26

## Tracker
ID | Workstream | Task | Owner | Priority | Start (working day) | End (working day) | Start date | End date | Depends on | Needs client input | Status | Notes
B1 | Brand | Collect logo variations (4 to 5) from client's team | Vinayak | Must | 0 | 5 | 2026-10-24 | 2026-10-30 |  | Yes | Not started | Client said the logo team will send 4 to 5 options
B2 | Brand | Collect client's colour and logo preferences | Vinayak | Must | 0 | 5 | 2026-10-24 | 2026-10-30 |  | Yes | Not started | Client has no brand guidelines yet
B3 | Brand | Lock palette (base, orange, yellow highlight, ink, grey, water blue) | Vinayak | Must | 0 | 2 | 2026-10-24 | 2026-10-27 |  | No | Not started | Chosen by Vinayak. See DESIGN.md
B4 | Brand | Lock typography and heading scale | Vinayak | Must | 2 | 4 | 2026-10-27 | 2026-10-29 | B3 | No | Not started | Build from DESIGN.md type scale
B5 | Brand | Lock iconography set (one line weight, one style) | Vinayak | Must | 3 | 5 | 2026-10-28 | 2026-10-30 | B3 | No | Not started | Phosphor icons used in current build
B6 | Brand | Show 2 luxury-and-convenience direction options to Rayansh | Vinayak | Must | 2 | 6 | 2026-10-27 | 2026-10-31 | B4 | No | Not started | Rayansh signs off before design work continues
B7 | Brand | Confirm patent wording: 'patent filed', not 'patented' | Rayansh | Must | 0 | 2 | 2026-10-24 | 2026-10-27 |  | Yes | Not started | Client said 'patented' but later said filed and not examined
C1 | Content | Receive presentation PDFs and product details | Omar (client) | Must | 0 | 5 | 2026-10-24 | 2026-10-30 |  | Yes | Not started | Promised by end of day 19 Oct. Chase
C2 | Content | Receive 'How we work' document (water flow, filter stages) | Omar (client) | Must | 0 | 5 | 2026-10-24 | 2026-10-30 |  | Yes | Not started | Client will share. Use only what is claimable
C3 | Content | Verify zero water wastage and 3LD claims with client's technical team | Rayansh | Must | 3 | 10 | 2026-10-28 | 2026-11-05 | C2 | Yes | Not started | Do not publish until verified. See Claims tab
C4 | Content | Product facts sheet: what can be said and how it is sourced | Vinayak | Must | 5 | 8 | 2026-10-30 | 2026-11-03 | C2 | No | Not started
C5 | Content | Write home page copy (consumer first) | Rayansh | Must | 5 | 10 | 2026-10-30 | 2026-11-05 | C4 | No | Not started | Headline: 'Get rid of the hassle.'
C6 | Content | Write builders page copy | Rayansh | Must | 5 | 10 | 2026-10-30 | 2026-11-05 | C4 | No | Not started
C7 | Content | Write comparison page copy (bottles, RO filters) | Rayansh | Must | 7 | 12 | 2026-11-02 | 2026-11-07 | C4 | No | Not started | Qualitative claims only until C3 is done
C8 | Content | Write environment page copy | Rayansh | Must | 7 | 12 | 2026-11-02 | 2026-11-07 | C4 | No | Not started
C9 | Content | Write contact and footer copy; replace placeholder email | Rayansh | Must | 10 | 14 | 2026-11-05 | 2026-11-10 |  | Yes | Not started | Client to confirm the contact address
D1 | Design | Moodboard: luxury and convenience reference set (5 to 8 sites) | Vinayak | Must | 2 | 5 | 2026-10-27 | 2026-10-30 | B6 | No | Not started | Avoid templates and generic SaaS look
D2 | Design | Bottle illustration: 20-litre jug (wide body, short neck) | Vinayak | Must | 2 | 5 | 2026-10-27 | 2026-10-30 | B3 | No | Not started | Replaces the battery-shaped drawing
D3 | Design | Hero scene: stick figure and branded dustbin | Vinayak | Must | 6 | 11 | 2026-10-31 | 2026-11-06 | D2 | No | Not started | Cap generic, dustbin Moya One branded
D4 | Design | Basement and control room illustration (isometric, basic, no tech detail) | Vinayak | Must | 6 | 11 | 2026-10-31 | 2026-11-06 | B5 | No | Not started | Client wants more machinery; keep it evocative, not a schematic
D5 | Design | Key screens: desktop and 390px mobile for home and builders | Vinayak | Must | 6 | 10 | 2026-10-31 | 2026-11-05 | D1 | No | Not started
D6 | Design | Component library: buttons, headings, cards, tables, nav | Vinayak | Must | 8 | 12 | 2026-11-03 | 2026-11-07 | B4 | No | Not started
D7 | Design | Client sign-off on design | Omar (client) | Must | 12 | 14 | 2026-11-07 | 2026-11-10 | D5 | Yes | Not started | Also needs Rayansh sign-off first
E1 | Build | Project setup: framework, GSAP, Lenis, fonts, icons | Harshita | Must | 7 | 8 | 2026-11-02 | 2026-11-03 | D6 | No | Not started | Next.js, Nuxt or Vite. Developer's choice; justify it in README
E2 | Build | Build home page (consumer first, builders teaser) | Harshita | Must | 8 | 12 | 2026-11-03 | 2026-11-07 | D5 | No | Not started
E3 | Build | Build builders page (with embedded MP4 video) | Harshita | Must | 10 | 13 | 2026-11-05 | 2026-11-09 | E1 | No | Not started | Video is an MP4 file, not a coded animation
E4 | Build | Build comparison hub and comparison pages | Harshita | Must | 10 | 14 | 2026-11-05 | 2026-11-10 | E1 | No | Not started
E5 | Build | Build environment, technology and contact pages | Harshita | Must | 11 | 14 | 2026-11-06 | 2026-11-10 | E1 | No | Not started
E6 | Build | Build interactions: recharge demo, app panel, how it works | Harshita | Must | 9 | 13 | 2026-11-04 | 2026-11-09 | D5 | No | Not started | Keep numbers labelled 'sample'
E7 | Build | Responsive QA at 390px and 1440px; no horizontal scroll | Harshita | Must | 12 | 14 | 2026-11-07 | 2026-11-10 | E2 | No | Not started
E8 | Build | Reduced-motion check and performance (Lighthouse mobile 85+) | Harshita | Must | 13 | 14 | 2026-11-09 | 2026-11-10 | E6 | No | Not started
F1 | Video | Video script and storyboard (building, pipe, kitchen unit, basement) | Rayansh's team | Must | 0 | 7 | 2026-10-24 | 2026-11-02 |  | Yes | Not started | Scope split between video and website still open.
F2 | Video | Receive client's reference animation | Omar (client) | Must | 0 | 3 | 2026-10-24 | 2026-10-28 |  | Yes | Not started | Promised by end of day 22 Oct
F3 | Video | Produce MP4 explainer (16:9, plus 9:16 cut for social) | Rayansh's team | Must | 7 | 21 | 2026-11-02 | 2026-11-18 | F1 | No | Not started | Biggest timeline risk. Confirm before kickoff
F4 | Video | Approve video cut with client | Omar (client) | Must | 21 | 23 | 2026-11-18 | 2026-11-20 | F3 | Yes | Not started
H1 | Launch | Client review round 1 on full site | Omar (client) | Must | 22 | 24 | 2026-11-19 | 2026-11-21 | E7 | Yes | Not started
H2 | Launch | Fix review round 1 feedback | Harshita | Must | 24 | 26 | 2026-11-21 | 2026-11-24 | H1 | No | Not started
H3 | Launch | Hosting set up (client hosting or Socialsect server) | Rayansh | Must | 22 | 26 | 2026-11-19 | 2026-11-24 |  | No | Not started | Client has no hosting yet
H4 | Launch | Point domain DNS, go live, check SSL | Harshita | Must | 26 | 27 | 2026-11-24 | 2026-11-25 | H2 | No | Not started
H5 | Launch | Hand over repo and domain ownership to client | Rayansh | Must | 27 | 28 | 2026-11-25 | 2026-11-26 | H4 | No | Not started | Domain must be in client's name
Formulas:
Start date = WORKDAY.INTL(Dashboard!$B3,[Start (working day)],"0000001")
End date = WORKDAY.INTL(Dashboard!$B3,[End (working day)],"0000001")

## Sitemap
Page | URL (proposed) | Audience | Priority | Purpose | Status | Notes
Home | / | Consumer, then builder | Phase 1 Must | Hero hook, convenience, quality, teaser for builders | Not started | Consumer sections first; builder sections later on the same page
How it works (consumer) | /b2c/how-it-works | Consumer | Phase 1 Must | Recharge, control unit in your kitchen, the flow | Not started | Interactive recharge demo lives here or on home
Water quality | /b2c/water-quality | Consumer | Phase 1 Should | Per-flat readings: TDS, pH, alkalinity, dissolved solids | Not started | Sample data only until client confirms parameters
Builders | /b2b/builders | Builder | Phase 1 Must | Installed at construction stage, no retrofit, space saved; embedded MP4 | Not started | Overview only, no technology detail
Installation | /b2b/installation | Builder | Phase 1 Should | Cellar control room, pipe to each flat, what the builder provides | Not started | Keep basic; no schematics
Compare (hub) | /compare | Consumer and builder | Phase 1 Must | Moya One vs bottled water vs RO filters | Not started | Qualitative labels only
Compare: bottled water | /compare/bottled-water | Consumer and builder | Phase 1 Must | Bottle routine vs one pipe | Not started
Compare: RO filters | /compare/ro-filters | Consumer and builder | Phase 1 Must | RO wastage and maintenance vs Moya One | Not started | Do not state a wastage figure until verified
Technology (overview) | /technology | Builder | Phase 1 Stretch | Overview of the system, patent filed, no technical depth | Not started | Wording per Claims tab
Environment | /environment | Both | Phase 1 Must | Plastic, emissions, zero liquid discharge | Not started | Client asked for this page
How we work | /how-we-work | Builder | Phase 1 Should | Process from installation to billing | Not started | Use client's 'How we work' document once received
Contact | /contact | Both | Phase 1 Must | Enquiry form, developer and consumer routes | Not started | Form only, no login
Compare: zero liquid discharge | /compare/zero-liquid-discharge | Both | Phase 1 Stretch | Water wastage angle, deeper comparison | Not started | Blocked until zero-wastage claim is verified
Compare: other comparisons (x6) | /compare/... | Both | Phase 1 Stretch | Further comparison pages Vinayak proposed | Not started | Count against the 15-page scope. Confirm with Rayansh
Insights / blog | /insights | Both | Later | Articles and videos | Not started | Deferred by client until builder handover
App and login | /app | Consumer | Later | Login with payment ID and OTP, payment history | Not started | Not in phase 1

## Client Inputs
# | Item needed from Omar (client) | Why it matters | Requested by | Status | Received on | Notes
1 | Logo variations (4 to 5) from client's logo team | Needed for home header and brand direction | Vinayak | Not started
2 | Colour and logo preferences | Lets us check the palette against his taste | Vinayak | Not started |  | Palette already chosen by Vinayak. Check fit, do not replace
3 | Presentation PDFs and product details | Source for product facts and copy | Rayansh | Not started |  | Promised 19 Oct
4 | 'How we work' document (water flow, filter stages) | Builders page and installation page copy | Rayansh | Not started |  | Use only claimable parts
5 | Reference animation video | Sets the style for the MP4 explainer | Rayansh | Not started |  | Promised 22 Oct
6 | Zero water wastage and 3LD: technical confirmation | Claims on comparison and environment pages | Vinayak | Not started |  | Do not publish until confirmed
7 | Hyderabad community details and permission to name it | Deployments strip | Vinayak | Not started |  | Use placeholder until approved
8 | Final brand name: Moya One or Moya1 | Domain, logo, trademark | Rayansh | Not started |  | Domain go-moya-one.com recommended
9 | Confirmation of domain spelling and purchase approval | Domain purchase | Rayansh | Not started
10 | Monthly plan terms (minimum occupancy, guarantee) for builder pages | Builders page content | Vinayak | Not started |  | Not in phase 1 price list. Confirm if needed

## Claims
Claim | Where it came from | Status | Action before publishing
Zero water wastage (unlike RO, which wastes about as much as it delivers) | Client, 19 Oct call | To confirm | Get written technical confirmation (C3)
3LD (zero liquid discharge) technology | Client, 22 Oct call | To confirm | Do not publish until verified
Patented technology | Client said 'patented' on 19 Oct, then 'filed, not yet examined' on 22 Oct | Do not use as stated | Use 'patent filed' until granted (B7)
Moya1 control-unit trademark | Client, 22 Oct call | Filed, not registered | Use the TM symbol only, not the registered mark
Hyderabad community, about 300 apartments, being installed | Client, 19 Oct call | To confirm | Placeholder until client approves naming
Deployed in India | Client, 19 Oct call | To confirm | Show India only, marked to confirm
UAE talks with two developers | Client, 19 Oct call | Do not publish | Do not name developers or show logos
Unlimited water on subscription | Client, 19 Oct call | To confirm | Confirm plan terms before saying 'unlimited'
Recharge from phone, like a mobile top-up | Client, 19 Oct call; headline concept | OK as concept | App is not built. Show as concept
Per-flat water-quality readings in app | Client, 19 Oct call | OK as concept | Label all readings as sample data
Best website in the world | Rayansh on 22 Oct call | Do not use | Not a claim the site can make
Minimum occupancy and minimum guarantee | Vinayak, 19 Oct call | Not confirmed | Do not publish until client confirms terms
Prices or rupee/dirham rates on site | Earlier concept drafts | Not in phase 1 | Remove. Price terms are not public yet